REPUBLIC OF TURKEY

THE REPORT OF THE FIRST PROJECT MEETING

KONYA / TURKEY

EXPLORING AND SHARING EUROPEAN - TURKISH COMMON AND DIFFERENT BODY LANGUAGES TO UNDERSTAND EACH OTHER BETTER.

THE FIRST MEETING OF EU COMENIUS SCHOOL PARTNERSHIP  PROJECT

KONYA / TURKEY

Mehmet TAKAR

English Teacher

EU Projects Coordinator

takar.mehmet@gmail.com

0554 249 96 00

THE REPORT OF THE FIRST PROJECT MEETING

22ND OCTOBER, 2012 ARRIVALS

23TH OCTOBER, 2012

MORNING SESSION

- Meeting all partners and introduction of the project

- Informative seminar on the description of the project, rationale of the project, impact of the project and objectives of the project

- Presentations of partner schools

- Brainstorming on the creation of the project logo and motto. Exhibition of drawings’ of Italian students, and photo albums of Italian partner.

- Common decision on the creation of project rooms at our schools and or classrooms, creation of project teams involving students and teachers of each partner country.

AFTERNOON SESSION

- Lunch at Lale High School, Meeting the Head Master, Hulusi YILDIZ, visit to Lale High School

- City tour, Mewlana Museum and understanding Mewlana philosophy LOVE PEACE AND TOLERANCE.

- Dinner at a traditional Turkish restaurant to taste Etli Ekmek which Konya is famous for.

- Back to the Hotel.

24th OCTOBER, 2012

MORNING SESSION

- Understanding of the Project and objectives

- Brainstorming on setting the goals of the next meetings.

- Understanding of Communication and Non-verbal Communication

- Brainstorming on the products of the project and activities for the dissemination

- Planning on the concent of the book and online tool, the division of the book as Common and Different Body languages of Europe and Turkey.

AFTERNOON SESSION

- Understanding and comparing body languages of Turkey and Europe by drama teachers from partner countries.

- Understanding each other via body languages, taking photos of samples of body languages and brainstorming on the meaning to everyone in the project.

- Planning the next three project meetings, brainstorming on the dates and the goals.

- Talking about the teachers and the students to participate to the second meeting in Milestone School, Kent.

25th October The Third Day of the Project Meeting

Morning Session

- Common decision on the Project Logo,  partners will cooperate to create the logo, Bulgaria, Italy, Czech Republic and The UK

- Common decision on the Project Motto, “Exploring and Sharing Body languages”

3. Sharing of the Project Tasks: All partners will research both common and different forms of non-verbal communication in their own local area and culture and explore and share these with each other at project meetings. Partners will take photos of body languages, gestures and facial expressions and write what each one means in their own culture by means of a power point presentation and photo albums. As the coordinator, Turkey will send out some examples of specific feelings, emotions, greetings, sitting positions, welcoming etc to all partners to be studied, explored and shared at the project meetings. Teachers and students will research their own cultures' body language, gestures and facial expressions by taking photos and writing the meanings of them.

TASKS

1. Turkey will be responsible for the creation of the e-mail group, and organizing communication between partners via e-mail, social networking and phones.  Turkey will also be responsible for the final report, coordinating all the participants in Turkey and the final presentation of partner schools. Turkey will research what is behind non-verbal communication and differentiate between different cultures and also the creation of the web site.

2. The UK will be responsible for writing the interim report, contributing to the final report and the analyzing the data from the partners’ project meetings and organizing the second project meeting in  Milestone school, Kent.

3. Italy will be responsible for designing the questionnaires on non-verbal communication to get the feedback from the students, staff and host partners after mobilities and send the questionnaires to the partners for consultation before official use. 20 questions will be in the questionnaire.

4. Austria will be responsible for the collection of all the pp. presentations of non-verbal communication and selecting the best examples for the final product, collecting all the photos and albums and drawings by students of partner countries and organizing the exhibition of the project products in the last meeting in Austria.

5. Portugal :responsible for writing sentences or phrases to give meaning to some specific body languages, gestures and facial expressions and finding out about games to illustrate non-verbal communication.

6. Bulgaria will be responsible for researching how non-verbal communication is used in animated and short films and  describing how body language, gestures and facial expressions are formed and what parts of the body are used to express non-verbal communication.

7Czech Republic will be responsible for finding out about communication in silent movies and clips with the description entitled to the movies in word documents.

Planning of other Project Dates: Meetings

UK:	22nd April-26th April 2013

ITALY:	16th Sep.-22nd Sep. 2013

AUSTRIA:	5th May-10th May 2014

- Power Point Presentations of All Partner Countries on Non-verbal Communication, samples of photos with meanings.

Afternoon Session

- Power Point Presentations of All Partner countries on Non-verbal Communication, digital data was shared with Austrian partner.

- Goals for the second meeting in Kent, Milestone School, The UK.

- Certificates of Participation

- Finishing the Project